## Projects
Node ID | Organization Name | Theme | Program | Project ID | Project Name | Reporting Year | Beneficiaries To-date | Success Title | Success Status | Budget Spent | Scorecard Report | How Success is Measured | Beneficiaries Type | Beneficiaries Details | Currency | Per Item Cost | Define 'Item' | Progress Percent Complete | Project Start Date | Project End Date | Original End Date | Project Status | Progress Flag | Delete Locked | Analytics Reporting | Project Complete | Budget Approved | Budget Spent To-date | Budget Status | Budget Flag | Expense Type
323 | Drainage | Drainage Infrastructure - Govt | Improve Infrastructure - Govt | PRJ0035 | Build New Catch Basin | 2020 | 250 | # of Catch Basins Built | On Track | 100,000 | No | # of Catch Basins Built | Items | Basins | $ | 400 | Catch basins | 75 | 01/01/2020 | 01/01/2020 | 12/31/2019 | Over Schedule and Budget | Red | Lock | Yes | No | 75,000 | 100,000 | More than 10% over Budget | Red | Capital
324 | Engineering | Construction - Govt | Improve Infrastructure - Govt | PRJ0037 | Build New Bridges | 2020 | 2 | # of Bridges Built | On Track | 2,608,000 | No | # of Bridges Built | Items | Bridges | $ | 1,304,000 | bridges | 25 | 04/01/2021 | 04/01/2021 | 05/29/2021 | Within Schedule and Budget | Green | Lock | Yes | No | 10,000,000 | 2,608,000 | Within Budget | Green | Operating
289 | District 2 Commissioner | Construction - Govt | Improve Infrastructure - Govt | PRJ0015 | Maintain County Roads and Bridges | 2020 | 230 |  | On Track | 9,000,000 | No | # of Bridges/ Roads Repaired | Items | # of Bridges/ Roads Repaired | $ | 39,130.43 | Roads/bridges | 77 | 01/01/2020 | 01/01/2020 | 12/31/2019 | Within Schedule and Budget | Green | Lock | Yes | No | 8,500,000 | 9,000,000 | Less than 10% over Budget | Yellow | Capital
290 | District 3 Commissioner | Construction - Govt | Improve Infrastructure - Govt | PRJ0016 | Maintain County Roads and Bridges | 2020 | 201 | # of Bridges/ Roads Repaired | On Track | 5,850,000 | No | # of Bridges/ Roads Repaired | Items |  | $ | 29,104.48 | roads/bridges | 60 | 01/01/2020 | 01/01/2020 | 12/31/2019 | Within Schedule and Budget | Green | Lock | Yes | No | 8,650,000 | 5,850,000 | Within Budget | Green | Capital
292 | Mayor's Office | Construction - Govt | Improve Infrastructure - Govt | PRJ0024 | Pass Infrastructure Improvement Laws | 2020 | 68 | # of Laws Passed | On Track | 2,000 | No | # of Laws Passed | Items |  | $ | 29.41 | Laws | 66 | 01/01/2020 | 01/01/2020 | 12/31/2019 | Within Schedule and Budget | Green | Lock | Yes | No | 11,200 | 2,000 | Within Budget | Green | Capital